## Task Sheet
Week | Name | Task | Deadline | Status | Notes
Week 1 | Mosharib | Add more loop-backs and long waits to the data (like X-Ray -> Triage again) | 13 Oct 2026 | Pending
Week 1 | Mosharib | Check columns: Case_ID, Activity, Timestamp | 13 Oct 2026 | Pending
Week 1 | Mosharib | Write a short README on how to run the script | 13 Oct 2026 | Pending
Week 1 | Mosharib | Commit everything to own branch | 13 Oct 2026 | Pending
Week 1 | Chandana | Set up the database (SQLite or MySQL) | 13 Oct 2026 | Pending
Week 1 | Chandana | Load Mosharib's CSV into the database | 13 Oct 2026 | Pending
Week 1 | Chandana | Write first cleaning SQL (no duplicates, time in order) | 13 Oct 2026 | Pending
Week 1 | Chandana | Commit SQL files to own branch | 13 Oct 2026 | Pending
Week 1 | Shubhangi | Load the CSV in Python (pandas) | 13 Oct 2026 | Pending
Week 1 | Shubhangi | Count different patient paths and loop-backs | 13 Oct 2026 | Pending
Week 1 | Shubhangi | Write 4 to 5 lines on what she found | 13 Oct 2026 | Pending
Week 1 | Shubhangi | Commit code and notes to own branch | 13 Oct 2026 | Pending
Week 1 | Varshini | Create repo and branches, share link | 13 Oct 2026 | Done
Week 1 | Varshini | Set up the task sheet | 13 Oct 2026 | Pending
Week 1 | Varshini | Draft the Work Distribution Document | 13 Oct 2026 | Pending
Week 1 | Varshini | Design Power BI dashboard layout on sample data | 13 Oct 2026 | Pending
How to use: change only the Status column (Pending / In progress / Done) and add Notes.